## Planning
| change the date below |  |  | MONTH -3 |  |  |  | MONTH -2 |  |  |  | MONTH -1
EVENT DATE | 2025-08-15 | ASAP | pre WEEK -12 | WEEK -12 | WEEK -11 | WEEK -10 | WEEK -9 | WEEK -8 | WEEK -7 | WEEK -6 | WEEK -5 | WEEK -4 | WEEK -3 | WEEK -2 | WEEK -1 | EVENT | WEEK +1 | WEEK +2 | WEEK +3 | WEEK +4
|  |  | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12
0. ORGANIZATIONAL FLOW
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1. PREPARE FIRST STEPS
Decide: connect to a bigger conference nearby (optional) |  | FALSE
Decide: find/delegate people to the task (job & roles) |  | FALSE
Decide: affiliated to MPB or independent event |  | FALSE
Notice: Mi Primer Bitcoin (MPB) doesn’t take sponsorships |  | FALSE
Decide: team up with Light/Full Nodes |  | FALSE | 2025-06-13: FALSE
Decide: mission versus finance |  | FALSE
Branding Policy |  | FALSE
Write onepager |  | FALSE
2. ROLE CLARITY
Local leader |  |  | 2025-05-16: FALSE
Local support group |  |  | 2025-05-16: FALSE
Create Telegram/Signal group for volunteers |  |  | 2025-06-27: FALSE
Create document with roles for volunteers |  |  | 2025-06-27: FALSE; 2025-07-11: FALSE
3. FINANCE
Budgetting |  |  | 2025-05-30: FALSE; 2025-06-06: FALSE; 2025-06-13: FALSE
Quotes
Ticket price |  |  | 2025-06-06: FALSE
Sponsorship
4. VENUE
Research options |  | FALSE | 2025-05-16: FALSE
Lock in venue |  |  | 2025-05-23: FALSE
Event liability Insurance |  |  | 2025-06-20: FALSE
Lock in equip partner |  |  | 2025-07-11: FALSE
Lock in labor services |  |  | 2025-06-20: FALSE
Lock in food truck |  |  | 2025-07-04: FALSE
5. TECH
Website |  |  | 2025-05-30: FALSE
Ticket sale |  |  | 2025-05-30: FALSE
Popup website |  |  | 2025-06-06: FALSE
6. MARKETING + BRANDING
Save the Date |  | FALSE | 2025-05-16: FALSE; 2025-05-23: FALSE; 2025-05-30: FALSE
Event date communication |  | FALSE
Theme |  |  | 2025-05-16: FALSE
Collaborations |  |  | 2025-05-16: FALSE
Press Release |  |  | 2025-06-06: FALSE; 2025-06-13: FALSE
Post about location |  |  | 2025-06-27: FALSE; 2025-07-04: FALSE
Copy for website |  |  | 2025-05-30: FALSE; 2025-06-06: FALSE
Trailer |  |  | 2025-06-13: FALSE
Testimonies |  |  | 2025-07-11: FALSE; 2025-08-15: FALSE
Flyer |  |  | 2025-06-06: FALSE; 2025-06-20: FALSE; 2025-07-11: FALSE
Throwback to previous Unconferences |  |  | 2025-07-04: FALSE
Reminder available Early Bird Tickets |  |  | 2025-06-20: FALSE
Speaker announcements |  |  | 2025-07-18: FALSE; 2025-07-25: FALSE; 2025-08-01: FALSE
Speaker Form send to current attendees list |  |  | 2025-07-11: FALSE; 2025-07-18: FALSE
Speaker Form on socials |  |  | 2025-07-04: FALSE; 2025-07-11: FALSE; 2025-07-18: FALSE
Schedule preparation |  |  | 2025-07-18: FALSE; 2025-07-25: FALSE
Schedule announcement |  |  | 2025-07-25: FALSE; 2025-08-01: FALSE
7. OPERATIONS
Find high name speakers |  |  | 2025-06-13: FALSE; 2025-06-27: FALSE
Speaker/workshops form on website |  |  | 2025-06-06: FALSE
Speaker/workshops decide/review |  |  | 2025-07-18: FALSE; 2025-07-25: FALSE
Contact with volunteers |  |  | 2025-06-27: FALSE
List of duty for volunteers |  |  | 2025-07-25: FALSE
Give tickets to volunteers |  |  | 2025-06-27: FALSE
Initial meeting workshops |  |  | 2025-07-04: FALSE; 2025-07-11: FALSE; 2025-07-18: FALSE
Operations during the day |  |  | 2025-06-27: FALSE
Print Schedule on-site |  |  | 2025-08-01: FALSE
Sent Tickets to speakers
Send email to all attendees with schedule |  |  | 2025-08-01: FALSE
Prepare slider background |  |  | 2025-08-01: FALSE
Print schedule |  |  | 2025-08-08: FALSE
Print OS Everything Unconf sheets |  |  | 2025-08-08: FALSE
8. MPB Props Kit
Merchandise |  |  | 2025-08-01: FALSE
Wristband |  |  | 2025-06-20: FALSE; 2025-07-25: FALSE; 2025-08-01: FALSE
MPB Flyers |  |  | 2025-07-25: FALSE
Banners |  |  | 2025-07-25: FALSE
Shirt for volunteer |  |  | 2025-07-04: FALSE
Scanner/phone |  |  | 2025-08-01: FALSE
Laptop |  |  | 2025-08-01: FALSE
Microphones |  |  | 2025-08-01: FALSE
Whiteboard
Projector |  |  | 2025-08-01: FALSE
9. Aftercare
Gratitude to speakers |  |  | 2025-08-22: FALSE
Feedback form to attendees |  |  | 2025-08-22: FALSE
Collect recordings, photo materials |  |  | 2025-08-22: FALSE

## Roles
Executive sponsor | name a
Event Lead | name b
Tech Lead | name c
Marketing/Communications | name d
Creatives | name e